2012 Budget Process

| Timeline | Activity | Responsibility |
| --- | --- | --- |
| Week of May 23 | Release budget instructions with specific directions and a description of process. Specific directions: - no new GPR funded positions, - no new operating or contractual expenses increases without funding recommendations, - prioritized list of capital projects Process description: - DOA will work with departments to develop GPR reduction scenarios - DOA will schedule meetings with departments to review reduction strategies - All department budgets will be finalized by August 26 although the technical review will be completed in advance of this deadline. | County Executive’s Office/DOA |
| Week of May 30 through August 26 | DOA meets with departments to develop and review departmental reduction strategies - Design strategies to achieve reductions of 5% and 10% for large departments and 2.5% and 5% for small departments based on a $2 million GPR threshold - Meet weekly with County Executive for briefings, policy directives, and tentative decisions | DOA and EA’s |
| August 26 | # Budget requests are finalized - All department requests will be finalized, including the technical review, by August 26. Completion time frames may vary depending on the complexity of the department’s budget. - Final submissions may include some or all of the elements described in the budget reduction strategies developed in consultation with DOA and the County Executive’s Office | Department Heads, DOA |
| September 7 | # Compilation Report Published - Consistent with the County’s budget ordinance, a compilation of the department requests will be released on September 7. | DOA |
| August 26 through September 26 | # County Executive Budget Decisions - DOA reviews departmental budget requests with County Executive to formally approve, deny, add or modify department recommendations - DOA works with departments on modifications requested by the County Executive - County Board and Executive hold appropriate public hearings seeking citizen input on budget development | DOA, County Executive, Department Heads |
| October 1 | # Executive Budget Released - County Executive releases Executive Recommended Budget on October 1 | County Executive |